## Agile Risk Register
AGILE RISK REGISTER
PROJECT | Leap-Learn Game
PROJECT MANAGER | Abdul Hadi + Syed Hunain Raza Zaidi
DATE OF LAST UPDATE | 2021-10-02
RISK ID NO. | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION STRATEGY | ACTION | OWNER | REASSESSMENT DATE | KEYS
| Risk Class Options | calculated risk and uncalculated risk | complete failure of project and too much delay | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | out-source of exiting risk to eliminate the problem | Choose from the drop-down menu. | Team members | 2021-10-02 | RISK CLASS | LEVEL | ACTION
1 | Timeline | Complete the project within timeline and select the team to divide the project into them to accomplish the task | Bad reputation & chances to lose client | 3 | 4 | 12 | some part of the project can be out-sourced | Transfer / Share | Team members & third party source |  | Solution | 1 | Avoid
2 | Budget | Cost Estimation | Providing right cost analysis to client will develop trust | 1 | 2 | 2 | Market cost survey | Exploit | Team members & client |  | Timeline | 2 | Exploit
3 | Resources | Building team for the project | Competitive & skilled developers will achieve the goal in prescribed time | 1 | 1 | 1 |  | Exploit | Team |  | Budget | 3 | Transfer / Share
4 | Resources | Gathering resources for project | Right resources will keep the project on track | 1 | 1 | 1 |  | Mitigate | Team and coordinator |  | Legislative | 4 | Mitigate
5 | Security | Game doesn't have any encryption or Firewall | Game can be hacked & it's code can be stolen | 5 | 5 | 25 |  | Accept with No Action | Team |  | Security | 5 | Accept with No Action
7 | Scope | Connectivity of Leap motion controller | Controller connectivity will ensure input of the game | 4 | 3 | 12 | Installing updated drivers for controller | Exploit | Team |  | Scope |  | Action
8 | Scope | Score calculation through implemented formulas | Formulas implementation will help user understand Physics concepts | 4 | 3 | 12 | Win/Loss description | Exploit | User
9 | Scope | Compatibility on all platforms | Unity a cross platform engine is used so the game can run on both Windows & Mac | 1 | 1 | 1 |  | Exploit | Team
10 | Scope | User friendly UI | Bad color sequence can create misunderstandings about game tasks & levels | 2 | 4 | 8 | Color picker tool | Exploit | Team
11 | Scope | Feature addition | Newer features can be added easily without interfering with current features | 3 | 3 | 9 |  | Mitigate | Team
12 | Scope | Maintenance | With time game can lag & would require downtime | 4 | 4 | 16 | Can be out-sourced | Mitigate | Team